## Sheet1
Task | Start Date | Days to complete | End Date
Identification of the base dynamic parameters of the quadrotor | 2021-02-01 | 14 | 2021-02-15
Designing the MPC | 2021-02-16 | 14 | 2021-03-02
Performing simulations with ROS and Gazebo using MPC | 2021-03-03 | 28 | 2021-03-31
Performing real experiments using MPC at LS2N | 2021-04-01 | 14 | 2021-04-15
Performing simulations with ROS and Gazebo using Trajectory optimization | 2021-04-16 | 28 | 2021-05-14
Performing real experiments using trajectory optimization at LS2N | 2021-05-15 | 14 | 2021-05-29
Comparing the performances of MPC and trajectory optimization (Closed-loop Vs Open-loop) | 2021-05-30 | 28 | 2021-06-27
Trying other control methods | 2021-06-28 | 28 | 2021-07-26
Writing the report | 2021-03-03 | 145 | 2021-07-26
Preparing the presentation | 2021-07-25 | 7 | 2021-08-01
Formulas:
End Date = [Start Date]+[Days to complete]